## Activity.WorkBreakdownStructure
WBS ID | Level | Task/Work Package Name | Duration (days) | Dependencies (WBS ID & Name) | DAVID DOMINGUEZ
1 |  | Plan career goals and audience (Deliverable) |  |  | CIS 4860
1.1 | Work Package | Define career objectives | 6
1.1.1 | Task | Research career goals | 2
1.1.2 | Task | Identrify required skills | 2 | 1.1.1 - Research career goals
1.1.3 | Task | Match personal strengths | 2 | 1.1.2 - Identify required skills
1.2 | Work Package | Audience and messaging | 6
1.2.1 | Task | Identify target audiences | 1
1.2.2 | Task | Define key messages | 2 | 1.2.1 - Identify target audience
1.2.3 | Task | Review with mentor | 1 | 1.2.2 - Define key messages
1.2.4 | Task | Finalize audience doc | 2 | 1.2.3 - Review with mentor
2 |  | Professional story (Deliverable)
2.1 | Work Package | Professional bio | 4
2.1.1 | Task | Draft professional bio | 2
2.1.2 | Task | Peer review | 1 | 2.1.1 - Draft professional bio
2.1.3 | Task | Finalize bio | 1 | 2.1.2 - Peer review bio
2.2 | Work Package | Resume preparation | 5
2.2.1 | Task | Update resume content | 2
2.2.2 | Task | Format resume | 2 | 2.2.1 - Update resume content
2.2.3 | Task | Export resume PDF | 1 | 2.2.2 - Format resume
2.3 | Work Package | Professional bio | 9
2.3.1 | Task | Select 3 projects | 1
2.3.2 | Task | Draft project writeups | 3 | 2.3.1 - Select 3 projects
2.3.3 | Task | Add visuals | 2 | 2.3.2 - Draft project writeups ¦¦
2.3.4 | Task | Review work samples | 2 | 2.3.3 - Add visuals
2.3.5 | Task | Finalize work samples | 1 | 2.3.4 - Review case studies
3 |  | Interactive portfolio website (Deliverable)
3.1 | Work Package | Planning & Structure | 2
3.1.1 | Task | Define sitemap | 1
3.1.2 | Task | Draft success metrics | 1 | 3.1.1 - Define sitemap
3.2 | Work Package | UI/UX design | 5
3.2.1 | Task | Wireframe pages | 2 | 3.1.2 - Draft success metrics
3.2.2 | Task | Mockup pages | 3 | 3.2.1 - Wireframe pages
3.3 | Work Package | Development | 12
3.3.1 | Task | Setup repo | 1
3.3.2 | Task | Build layout | 2 | 3.3.1 - Setup repo
3.3.3 | Task | Implement Home/About | 3 | 3.3.2 - Build layout
3.3.4 | Task | Implement portfolio | 3 | 3.3.2 - Build layout
3.3.5 | Task | Implement Resume/Contact | 3 | 3.3.3 - Implement Home/About
3.4 | Work Package | Integration | 4
3.4.1 | Task | Add resume download | 1 | 3.3.5 - Implement Resume/Contact
3.4.2 | Task | Integrate LinkedIn/Github | 1 | 3.3.5 - Implement Resume/Contact
3.4.3 | Task | Add contact form | 2 | 3.3.5 - Implement Resume/Contact
4 |  | Networking toolkit (Deliverable)
4.1 | Work Package | Resume PDF | 3
4.1.1 | Task | Proofread resume content
4.1.2 | Task | Design PDF layout |  | 4.1.1 - Proof resume content
4.2 | Work Package | LinkedIn Integration | 3
4.2.1 | Task | Update LinkedIn profile | 2
4.2.2 | Task | Cross-link website | 1 | 4.2.1 - Update LinkedIn Profile
4.3 | Work Package | QR Code | 1
4.3.1 |  | Generate QR code | 1
5 |  | Launch and feedback cycle (Deliverable)
5.1 | Work Package | Collect Feedback for Improvements | 6
5.1.1 | Task | Browser testing | 2 | 3.4.3 - Add contact form
5.1.2 | Task | Device testing | 2 | 5.1.1 - Browser testing
5.1.3 | Task | Accessibility check | 2 | 5.1.2 - Device testing
5.2 | Work Package | Deployment | 4
5.2.1 | Task | Setup hosting | 2
5.2.2 | Task | Deploy to domain | 2 | 5.2.1 - Setup hosting
5.3 | Work Package | Feedback Collection | 6
5.3.1 | Task | Collect peer feedback | 2 | 5.2.2 - Deploy to domain
5.3.2 | Task | Collect mentor feedback | 2 | 5.2.2 - Deploy to domain
5.3.3 | Task | Summarize improvements | 2 | 5.3.1 - Collect peer feedback ¦¦ 5.3.2 - Collect mentor feedback